## Priority Summary
TENU.WORLD — RESTE-À-FAIRE DASHBOARD
Last reconciled: 2026-04-18 ¦ Week 2-3 of build ¦ Soft launch 11 May 2026
BY PRIORITY
Priority | Open count | Description
P0 (Blocker) | 14 | Must clear before soft launch 11 May 2026
P1 (Launch) | 20 | Required during Week 2-4 build window
P2 (Post-launch) | 7 | Can ship after first paying cohort
BY DOMAIN
Domain | Total | P0 | P1 | P2
Agents | 5 | 3 | 2 | 0
Backend | 9 | 8 | 1 | 0
Brand | 4 | 1 | 3 | 0
Database | 2 | 2 | 0 | 0
Finance | 2 | 0 | 1 | 1
Frontend | 5 | 2 | 2 | 1
Governance | 1 | 0 | 0 | 1
Infrastructure | 10 | 8 | 2 | 0
Legal | 12 | 11 | 1 | 0
Marketing | 6 | 0 | 5 | 1
Mobile | 8 | 0 | 2 | 6
Paperclip | 35 | 0 | 35 | 0
Pipeline | 4 | 3 | 1 | 0
Pricing | 1 | 1 | 0 | 0
Product | 2 | 0 | 0 | 2
QA | 5 | 2 | 3 | 0
i18n | 7 | 0 | 6 | 1
TOTAL | 118 | 41 | 64 | 13
BY OWNER
Owner | Total | P0 | P1 | P2
Claude Cowork | 53 | 25 | 20 | 8
Dr Mubashir | 30 | 16 | 9 | 5
(Paperclip legacy) | 35 | 0 | 35 | 0
BY STATUS
Status | Count
Done | 52
In Progress | 8
To Do | 33
Cancelled | 25
CRITICAL PATH TO SOFT LAUNCH (11 May 2026)
T-005 Brevo templates → T-020 Pipeline 1 payment→report → T-414 Dispute Sonnet → T-421 Consents
→ T-422 Google OAuth External → T-423 Magic Link template → T-420 T-103 core tests
→ T-426 E2E Stripe→Brevo → T-418 Stripe Tax + OSS → T-034 FR avocat opinion
→ T-427 médiateur decision → FIRST PAYING USER

## Governance Model
TENU.WORLD — OPTION C GOVERNANCE MODEL
Layer | Actor | Adapter | Role | Budget / Cost Control
Strategic Review | CEO Agent (Sonnet) | claude_local | Weekly strategic review: validates priorities, flags risks, reviews KPIs. Runs once per week on Monday. | $15/month cap. ~$1-2 per review run.
Technical Governance | CTO Agent (Sonnet) | claude_local | Code review gatekeeper: reviews PRs, validates architecture decisions, approves scope changes. Runs on-demand when Dr Mubashir triggers. | $20/month cap ($8.95 remaining). ~$1-3 per run.
Execution | Dr Mubashir + Claude Cowork | N/A (this session) | ALL code, config, deployment, testing, content writing. The human-AI pair does every deliverable. | Included in Claude subscription.
Monitoring | Telegram Bot + LaunchAgent | paperclip-monitor.py | Automated alerts: failed runs, budget breaches, stalled work. Digest every 30 min. | Free (runs locally).
DECISION RULE
CEO runs weekly. CTO runs only when you say so. Everything else is you + me.
WHAT CHANGES FROM CURRENT SETUP
Before | After
10 agents, 8 on Ollama (all failing) | 2 agents on Sonnet (governance only)
gemma4:e4b doing dev tasks (0% success) | Claude Cowork does all dev (100% success)
No systematic tracking | Excel reste-à-faire + Paperclip issues
Ad hoc follow-up | Weekly CEO review + on-demand CTO review

## Reste-à-Faire
ID | Domain | Task | Owner | Status | Priority | Deadline | Dependency | Deliverable | Notes
T-001 | Infrastructure | Set up Supabase project (create project, run 001_schema.sql migration) | Dr Mubashir | Done | P0 | 2026-04-17 | None | Supabase project URL + anon key in .env.local | [Session 8 04/16] Migrations 001+002 both run in Supabase
T-002 | Infrastructure | Create Cloudflare R2 bucket (tenu-photos-eu, EU region, private) | Dr Mubashir | Done | P0 | 2026-04-17 | None | R2 account ID + access keys in .env.local | [Session 7] R2 bucket created, keys in .env.local
T-003 | Infrastructure | Configure Stripe account (products, prices, 6 discount codes, webhook endpoint) | Dr Mubashir | Done | P0 | 2026-04-17 | None | Stripe API keys + price IDs in .env.local | [Session 7-8] Stripe test keys configured, dynamic pricing (no fixed products), webhook endpoint set
T-004 | Infrastructure | Deploy to Vercel (connect GitHub repo, set env vars, verify tenu.world DNS) | Dr Mubashir | Done | P0 | 2026-04-18 | T-001, T-002, T-003 | tenu.world live with Next.js app | [Session 6] Vercel deployed, tenu.world live, DNS configured
T-005 | Infrastructure | Configure Brevo (domain verification, 3 email templates: report EN, report FR, 14-day survey) | Dr Mubashir | In Progress | P1 | 2026-04-20 | T-004 | Brevo API key in .env.local + templates live | DNS records on Namecheap ¦ [2026-04-18] Brevo SMTP in Supabase Auth configured (#46). Domain verify + 3 templates still open.
T-010 | i18n | Complete hi.json (Hindi) dictionary | Claude Cowork | To Do | P1 | 2026-04-22 | None | src/lib/i18n/dictionaries/hi.json | Native speaker review needed
T-011 | i18n | Complete ja.json (Japanese) dictionary | Claude Cowork | To Do | P1 | 2026-04-22 | None | src/lib/i18n/dictionaries/ja.json | Native speaker review needed
T-012 | i18n | Complete es.json (Spanish) dictionary | Claude Cowork | To Do | P1 | 2026-04-22 | None | src/lib/i18n/dictionaries/es.json
T-013 | i18n | Complete it.json (Italian) dictionary | Claude Cowork | To Do | P1 | 2026-04-22 | None | src/lib/i18n/dictionaries/it.json
T-014 | i18n | Complete uk.json (Ukrainian) dictionary | Claude Cowork | To Do | P2 | 2026-04-25 | None | src/lib/i18n/dictionaries/uk.json
T-015 | i18n | Native speaker review: zh.json (Chinese) | Dr Mubashir | To Do | P1 | 2026-04-29 | None | Reviewed zh.json committed | Find reviewer in Chinese student network
T-016 | i18n | Native speaker review: ar.json (Arabic) | Dr Mubashir | To Do | P1 | 2026-04-29 | None | Reviewed ar.json committed | Find reviewer via ISOC or mosque network
T-020 | Pipeline | Build Pipeline 1: Stripe webhook → Supabase user fetch → R2 photo fetch → Claude Haiku scan → PDF generation → R2 upload → Brevo email | Claude Cowork | In Progress | P0 | 2026-04-23 | T-001, T-002, T-003, T-005 | src/app/api/webhooks/stripe/route.ts (extended) | This is the core revenue path ¦ [2026-04-18] Risk-scan v2 on /api/ai/scan live (#22, #33). PDF gen + R2 upload + Brevo send still pending (#25).
T-021 | Pipeline | Build Pipeline 2: Dispute add-on → Claude Sonnet letter → PDF append → R2 upload → Brevo email | Claude Cowork | In Progress | P0 | 2026-04-25 | T-020 | src/app/api/ai/dispute/route.ts (extended) | [Sync 04/15 15:54] Paperclip: done ¦ [2026-04-18] Dispute v2 spec shipped, /api/ai/dispute scaffold in place (#30). Sonnet handler still being finalised.
T-022 | Pipeline | Build Pipeline 3: Supabase scheduled function → 14-day Brevo outcome survey → Supabase update | Claude Cowork | To Do | P1 | 2026-04-29 | T-020, T-005 | Supabase Edge Function or cron | Outcome data feeds Year 1 metrics
T-030 | Legal | Implement R2 signed URLs (no public photo access, 1-hour expiry) | Claude Cowork | Done | P0 | 2026-04-21 | T-002 | src/lib/storage/r2-upload.ts updated | Critical for GDPR compliance ¦ [2026-04-17] R2 signed URLs + evidence chain (sha256+EXIF) live on 0240bec (#23).
T-031 | Legal | Implement 30-day photo deletion (Supabase cron + R2 delete) | Claude Cowork | To Do | P0 | 2026-04-23 | T-001, T-002 | Supabase Edge Function + R2 lifecycle | GDPR data retention requirement
T-032 | Legal | Create privacy policy page (/privacy) — FR + EN | Claude Cowork | Done | P0 | 2026-04-21 | None | src/app/privacy/page.tsx | [Sync 04/17 12:18] Paperclip: done ¦ [2026-04-17] /legal/privacy live FR+EN with DRAFT banner (#17).
T-033 | Legal | Create terms of service page (/terms) — FR + EN | Claude Cowork | Done | P0 | 2026-04-21 | None | src/app/terms/page.tsx | [Sync 04/17 12:18] Paperclip: done ¦ [2026-04-17] /legal/terms live FR+EN with DRAFT banner (#17).
T-034 | Legal | Commission FR avocat opinion (droit locatif, €500-1000) | Dr Mubashir | To Do | P0 | 2026-04-25 | None | Written legal opinion PDF | Barreau de Paris or HEC network
T-035 | Legal | Commission UK solicitor opinion (Legal Services Act 2007, £400-800) | Dr Mubashir | Cancelled | P0 | 2026-04-25 | None | Written legal opinion PDF | Law Society directory ¦ [2026-04-17] UK disabled at launch per pricing lock. Revisit after first FR cohort outcome data.
T-036 | Legal | Add 'not legal advice' checkbox before report delivery | Claude Cowork | In Progress | P1 | 2026-04-23 | T-020 | UI checkbox + Supabase consent log | Legal requirement per C1 risk ¦ [2026-04-18] Consent touchpoints scoped (#29). Blocked by #47 Google OAuth External + #48 Magic Link template.
T-040 | QA | End-to-end test: login → new inspection → photo capture → submit → report view | Claude Cowork | To Do | P0 | 2026-04-27 | T-001, T-002, T-004 | Test report in /docs/qa/ | Manual test, then automate
T-041 | QA | Test RTL layout (Arabic, Urdu) on all pages | Claude Cowork | To Do | P1 | 2026-04-29 | T-010 | Screenshot comparisons | Tailwind RTL plugin
T-042 | QA | Test Stripe checkout flow with all 6 discount codes | Dr Mubashir | To Do | P1 | 2026-04-27 | T-003, T-020 | All codes validated in test mode | Use Stripe test cards ¦ [2026-04-17] Pricing model changed to 5-tier grid (T-409). Discount codes reset. Re-validate in test mode.
T-043 | QA | Test Claude Haiku risk scan with sample room photos | Claude Cowork | Done | P1 | 2026-04-25 | T-001 | JSON risk output validated | [Sync 04/15 15:54] Paperclip: done ¦ [2026-04-17] Haiku scan grille JSON validated against Décret 87-712 references.
T-050 | Mobile | Initialize Capacitor iOS project from Next.js build | Claude Cowork | Done | P2 | 2026-05-06 | T-004, T-040 | ios/ directory with Xcode project | [Sync 04/15 15:54] Paperclip: done ¦ [2026-04-17] Capacitor 6 iOS scaffold (#24, #49). TestFlight build still pending.
T-051 | Mobile | Configure native camera plugin for iOS | Claude Cowork | Done | P2 | 2026-05-08 | T-050 | Camera works in iOS simulator | [Sync 04/15 15:54] Paperclip: done ¦ [2026-04-17] Camera plugin wired. Confirmed in simulator.
T-052 | Mobile | TestFlight build + internal testing | Dr Mubashir | To Do | P2 | 2026-05-13 | T-051 | TestFlight link shared | Apple Developer account needed
T-053 | Mobile | Initialize Capacitor Android project from Next.js build | Claude Cowork | Done | P2 | 2026-05-06 | T-004, T-040 | android/ directory with Gradle project | [Sync 04/15 15:54] Paperclip: done ¦ [2026-04-17] Capacitor 6 Android scaffold (#24, #49).
T-054 | Mobile | Configure native camera plugin for Android | Claude Cowork | Done | P2 | 2026-05-08 | T-053 | Camera works in Android emulator | [Sync 04/15 15:54] Paperclip: done ¦ [2026-04-17] Camera plugin wired. Confirmed in emulator.
T-055 | Mobile | Play Store internal test track | Dr Mubashir | To Do | P2 | 2026-05-13 | T-054 | Internal test link | Google Play Console account needed
T-060 | Marketing | Create waitlist landing page on tenu.world | Claude Cowork | To Do | P1 | 2026-04-20 | T-004 | Live page with email capture | Brevo form or Tally embed
T-061 | Marketing | Post in Chinese student community (Facebook/WeChat) — demand validation | Dr Mubashir | To Do | P1 | 2026-04-22 | T-060 | 20+ signups in 48h = green light | Use ZH copy from GTM plan
T-062 | Marketing | Post in Reddit r/france (LOCATAIRE25 code) | Dr Mubashir | To Do | P1 | 2026-04-24 | T-060 | Signup count tracked
T-063 | Marketing | Contact 3 UK ISOC housing officers (UMMAH25 code) | Dr Mubashir | To Do | P2 | 2026-04-29 | T-060 | 3 emails sent, responses tracked | UCL, King's, Manchester
T-064 | Marketing | Draft launch announcement for all 5 target communities | Claude Cowork | To Do | P1 | 2026-04-27 | None | 5 posts in ZH, AR, UR, EN, FR | Community-specific messaging
T-070 | Finance | Set up Global Apex bank tracking for Tenu expenses | Dr Mubashir | To Do | P1 | 2026-04-22 | None | Expense ledger (Excel or accounting tool) | Separate cost center for Tenu
T-071 | Finance | First monthly financial report (costs vs. projections) | Dr Mubashir | To Do | P2 | 2026-05-15 | T-070 | Financial report PDF/XLSX | Compare to 04-Financial projections
T-072 | Governance | Sign Make.com EU DPA (if any Make.com usage remains) | Dr Mubashir | Cancelled | P2 | 2026-04-29 | None | Signed DPA on file | May not be needed if pipeline is all in-code ¦ [2026-04-15] Pipeline moved fully in-code (Next.js API routes). No Make.com usage remains.
T-080 | Agents | Reconfigure Paperclip: pause all Ollama agents, keep CEO + CTO active | Dr Mubashir | Done | P0 | 2026-04-15 | None | SQL executed, agents reconfigured | SQL provided in this workbook ¦ [2026-04-17] Option 2 executed (#18). All 10 agents paused, 14 issues closed. Dashboard-only mode.
T-081 | Agents | Create CEO weekly review issue (Monday cadence) | Dr Mubashir | Cancelled | P1 | 2026-04-17 | T-080 | Recurring Paperclip issue | CEO reviews priorities, flags risks ¦ [2026-04-17] CEO weekly review retired with the agent fleet. Governance runs off the dashboard + Claude Cowork session cadence.
T-082 | Agents | Set up Telegram bot for monitoring (BotFather → token + chat_id) | Dr Mubashir | In Progress | P0 | 2026-04-16 | None | ~/.paperclip-monitor.env populated | Then: launchctl load the plist ¦ [2026-04-17] Telegram push channel scoped (#32). Token + chat_id procurement open.
T-083 | Agents | Activate LaunchAgent for paperclip-monitor | Dr Mubashir | Done | P0 | 2026-04-16 | T-082 | Monitor running every 5 min | launchctl load ~/Library/LaunchAgents/com.globalapex.paperclip-monitor.plist ¦ [2026-04-17] governance-sync LaunchAgent running every 30 min.
T-084 | Paperclip | Hire your first engineer and create a hiring plan | Head of HR | Cancelled | P1 |  |  |  | [Auto-added from Paperclip 04/15] ¦ [2026-04-17] Paperclip agent fleet retired (#18). Dashboard-only mode — this auto-generated entry is obsolete.
T-086 | Paperclip | Set up technical foundation and development environment | CTO | Cancelled | P1 |  |  |  | [Auto-added from Paperclip 04/15] ¦ [2026-04-17] Paperclip agent fleet retired (#18). Dashboard-only mode — this auto-generated entry is obsolete.
T-089 | Paperclip | Define and build the first MVP app or AI agent | CTO | Cancelled | P1 |  |  |  | [Auto-added from Paperclip 04/15] ¦ [2026-04-17] Paperclip agent fleet retired (#18). Dashboard-only mode — this auto-generated entry is obsolete.
T-093 | Paperclip | CTO: Reactivate and deliver Week 2-4 technical roadmap for Tenu.World | CTO | Cancelled | P1 |  |  |  | [Auto-added from Paperclip 04/15] ¦ [2026-04-17] Paperclip agent fleet retired (#18). Dashboard-only mode — this auto-generated entry is obsolete.
T-098 | Paperclip | [Marketing] Week 4 launch plan: community outreach across 5 target segments | Head of Marketing | Cancelled | P1 |  |  |  | [Auto-added from Paperclip 04/15] ¦ [2026-04-17] Paperclip agent fleet retired (#18). Dashboard-only mode — this auto-generated entry is obsolete.
T-104 | Paperclip | [Finance] Weekly KPI dashboard and first monthly board financial report | Head of Finance | Cancelled | P1 |  |  |  | [Auto-added from Paperclip 04/15] ¦ [2026-04-17] Paperclip agent fleet retired (#18). Dashboard-only mode — this auto-generated entry is obsolete.
T-111 | Paperclip | [HR] Build agent hiring pipeline and coordinate department head onboarding | Head of HR | Cancelled | P1 |  |  |  | [Sync 04/15 15:54] Paperclip: in_progress ¦ [2026-04-17] Paperclip agent fleet retired (#18). Dashboard-only mode — this auto-generated entry is obsolete.
T-119 | Paperclip | [Product] 6-feature roadmap and Week 2-4 specs for Tenu.World | Head of Product | Cancelled | P1 |  |  |  | [Sync 04/15 15:54] Paperclip: in_progress ¦ [2026-04-17] Paperclip agent fleet retired (#18). Dashboard-only mode — this auto-generated entry is obsolete.
T-128 | Paperclip | [Web] Complete i18n dictionaries: hi.json, ja.json, es.json, it.json, uk.json | Senior Web Developer | Cancelled | P1 |  |  |  | [Auto-added from Paperclip 04/15] ¦ [2026-04-17] Paperclip agent fleet retired (#18). Dashboard-only mode — this auto-generated entry is obsolete.
T-138 | Paperclip | [Web] Integrate Brevo transactional email for report delivery and follow-up | Senior Web Developer | Cancelled | P1 |  |  |  | [Auto-added from Paperclip 04/15] ¦ [2026-04-17] Paperclip agent fleet retired (#18). Dashboard-only mode — this auto-generated entry is obsolete.
T-149 | Paperclip | [iOS] Prepare App Store submission: icons, splash screens, metadata | Senior iOS Developer | Cancelled | P1 |  |  |  | [Auto-added from Paperclip 04/15] ¦ [2026-04-17] Paperclip agent fleet retired (#18). Dashboard-only mode — this auto-generated entry is obsolete.
T-161 | Paperclip | [Android] Prepare Play Store submission: icons, screenshots, metadata | Senior Android Developer | Cancelled | P1 |  |  |  | [Auto-added from Paperclip 04/15] ¦ [2026-04-17] Paperclip agent fleet retired (#18). Dashboard-only mode — this auto-generated entry is obsolete.
T-174 | Paperclip | [Web] Build in-code payment-to-delivery pipeline (no Make.com) | Senior Web Developer | Cancelled | P1 |  |  |  | [Auto-added from Paperclip 04/15] ¦ [2026-04-17] Paperclip agent fleet retired (#18). Dashboard-only mode — this auto-generated entry is obsolete.
T-188 | Paperclip | Complete i18n dictionaries for hi, ja, es, pt, ko | Senior Web Developer | Cancelled | P1 |  |  |  | [Auto-added from Paperclip 04/15] ¦ [2026-04-17] Paperclip agent fleet retired (#18). Dashboard-only mode — this auto-generated entry is obsolete.
T-203 | Paperclip | Integrate Brevo transactional email for report delivery and 14-day follow-up | Senior Web Developer | Done | P1 |  |  |  | [Sync 04/15 15:54] Paperclip: done
T-219 | Paperclip | End-to-end QA: full inspection flow from onboarding to report download | Senior Web Developer | Cancelled | P1 |  |  |  | [Auto-added from Paperclip 04/15] ¦ [2026-04-17] Paperclip agent fleet retired (#18). Dashboard-only mode — this auto-generated entry is obsolete.
T-236 | Paperclip | Capacitor iOS: build setup, native camera integration, and TestFlight build | Senior iOS Developer | Cancelled | P1 |  |  |  | [Sync 04/15 15:54] Paperclip: done ¦ [2026-04-17] Paperclip agent fleet retired (#18). Dashboard-only mode — this auto-generated entry is obsolete.
T-254 | Paperclip | Capacitor Android: build setup, native camera integration, and internal test track | Senior Android Developer | Cancelled | P1 |  |  |  | [Sync 04/15 15:54] Paperclip: done ¦ [2026-04-17] Paperclip agent fleet retired (#18). Dashboard-only mode — this auto-generated entry is obsolete.
T-273 | Paperclip | Investigate and recover Senior iOS Developer and Senior Android Developer agents (error state) | CTO | Cancelled | P1 |  |  |  | [Auto-added from Paperclip 04/15] ¦ [2026-04-17] Paperclip agent fleet retired (#18). Dashboard-only mode — this auto-generated entry is obsolete.
T-293 | Paperclip | Investigate and recover Senior iOS Developer and Senior Android Developer agents (error state) | CTO | Cancelled | P1 |  |  |  | [Auto-added from Paperclip 04/15] ¦ [2026-04-17] Paperclip agent fleet retired (#18). Dashboard-only mode — this auto-generated entry is obsolete.
T-314 | Paperclip | [CEO ESCALATION] Systemic agent error: CTO + iOS + Android developers all crashing on startup | unassigned | Cancelled | P1 |  |  |  | [Auto-added from Paperclip 04/15] ¦ [2026-04-17] Paperclip agent fleet retired (#18). Dashboard-only mode — this auto-generated entry is obsolete.
T-315 | Paperclip | CEO: Document session progress and update Excel tracker | CEO | Cancelled | P1 |  |  |  | [Auto-added from Paperclip 04/15] ¦ [2026-04-17] Paperclip agent fleet retired (#18). Dashboard-only mode — this auto-generated entry is obsolete.
T-316 | Paperclip | CEO: Morning check-in 2026-04-16 — catch-up sprint begins | CEO | Cancelled | P1 |  |  |  | [Auto-added from Paperclip 04/16] ¦ [2026-04-17] Paperclip agent fleet retired (#18). Dashboard-only mode — this auto-generated entry is obsolete.
T-090 | Frontend | Rewrite inspection/new form: owner, tenants, contract, property, zone tendue, French UI | Claude Cowork | Done | P0 | 2026-04-16 |  | src/app/inspection/new/page.tsx | [Session 8 04/16] Full form with 6 sections, zone tendue auto-detect from postal code
T-091 | Frontend | Build element rating UI (TB/B/M/MV per element, auto-save, progress bar) | Claude Cowork | Done | P0 | 2026-04-16 |  | src/components/inspection/ElementRatingPanel.tsx | [Session 8 04/16] Integrated in capture flow
T-092 | Backend | Build /api/inspection/create route (owner, tenants, contract, zone tendue, rooms) | Claude Cowork | Done | P0 | 2026-04-16 |  | src/app/api/inspection/create/route.ts | [Session 8 04/16] Server-side zone tendue detection
T-094 | Backend | Build /api/inspection/ratings route (GET + POST upsert per element) | Claude Cowork | Done | P0 | 2026-04-16 |  | src/app/api/inspection/ratings/route.ts | [Session 8 04/16] Ownership verification via room->inspection->user
T-095 | Backend | Build zone tendue postal code lookup utility (1100+ postal codes from Décret 2013-392) | Claude Cowork | Done | P0 | 2026-04-16 |  | src/lib/geo/zone-tendue.ts | [Session 8 04/16] Notice period auto-calc
T-096 | Backend | Build element checklist definitions per room type (10 standard + kitchen/bathroom extras) | Claude Cowork | Done | P0 | 2026-04-16 |  | src/lib/inspection/elements.ts | [Session 8 04/16] Matches official état des lieux templates
T-097 | Database | Run migration 002: tenants table, element_ratings table, owner/contract/property columns on inspections | Dr Mubashir | Done | P0 | 2026-04-16 | T-001 | supabase/migrations/002_owner_contract_tenants.sql | [Session 8 04/16] Both 001+002 run in SQL Editor
T-099 | Infrastructure | Configure Stripe webhook endpoint (checkout.session.completed) + signing secret | Dr Mubashir | Done | P0 | 2026-04-16 | T-003 | STRIPE_WEBHOOK_SECRET in .env.local + Vercel | [Session 8 04/16] whsec_ key configured
T-100 | Paperclip | CTO-01 Grille de vetuste data file (JSON) | CTO | Done | P1 |  |  |  | [Sync 04/17 12:18] Paperclip: done
T-102 | Paperclip | CEO-02 Cold outreach DM template FR (400 chars max) | CEO | Done | P1 |  |  |  | [Sync 04/17 12:18] Paperclip: done
T-105 | Paperclip | CEO-03 Politique de confidentialite FR | CEO | Done | P1 |  |  |  | [Sync 04/17 12:18] Paperclip: done
T-109 | Paperclip | CTO-05 Security checklist for API routes | CTO | Done | P1 |  |  |  | [Sync 04/17 12:18] Paperclip: done
T-114 | Paperclip | CEO-05 CGU FR | CEO | Done | P1 |  |  |  | [Sync 04/17 12:18] Paperclip: done
T-120 | Paperclip | CEO-07 Politique de remboursement FR | CEO | Done | P1 |  |  |  | [Sync 04/17 12:18] Paperclip: done
T-127 | Paperclip | CEO-08 Refund Policy EN (translate FR) | CEO | Done | P1 |  |  |  | [Sync 04/17 12:18] Paperclip: done
T-135 | Paperclip | CTO-02 ADR-001 Grille de vetuste integration | CTO | Done | P1 |  |  |  | [Sync 04/17 12:18] Paperclip: done
T-144 | Paperclip | CTO-03 Prompt spec for /api/ai/scan v2 (Haiku) | CTO | Done | P1 |  |  |  | [Sync 04/17 12:18] Paperclip: done
T-154 | Paperclip | CTO-04 Prompt spec for /api/ai/dispute v2 (Sonnet) | CTO | Done | P1 |  |  |  | [Sync 04/17 12:18] Paperclip: done
T-165 | Paperclip | CTO-06 T-103 end-to-end smoke test plan | CTO | Done | P1 |  |  |  | [Sync 04/17 12:18] Paperclip: done
T-177 | Paperclip | CEO-01 PDF disclaimer footer (FR+EN, 25 words each) | CEO | Done | P1 |  |  |  | [Sync 04/17 12:18] Paperclip: done
T-400 | Brand | Extract and implement Tenu Identity v1 — disc mark + portal mark + parametric TenuMark component (11 containers) | Claude Cowork | Done | P1 | 2026-04-18 | None | public/brand/mark-disc.svg, mark-portal.svg, src/components/brand/TenuMark.tsx | [2026-04-18] Issues #62 + #63 shipped. theme.css untouched at this stage.
T-401 | Brand | Apple-crisp palette repaint across global surfaces — emerald CTA, ink, canvas + Identity v1 navy/paper chrome | Claude Cowork | Done | P1 | 2026-04-17 | None | src/app/theme.css palette + semantic tokens | [2026-04-17] Issue #59. WCAG 2.2 AA contrast verified.
T-402 | Brand | Extract design tokens into theme.css + .t-* component classes for web + PDF + email reuse | Claude Cowork | Done | P1 | 2026-04-17 | T-401 | src/app/theme.css, docs/THEMING.md | [2026-04-17] Issue #60. Two-layer architecture (palette → semantic).
T-403 | Marketing | Rewrite landing homepage copy in anxiety-to-relief voice (FR + EN) | Claude Cowork | Done | P1 | 2026-04-17 | None | src/app/[locale]/page.tsx | [2026-04-17] Issue #61. Register will get v1.1 alignment pass in a separate sweep.
T-404 | Brand | Brand Guidelines v1.0 → v1.1 — full professional services register (cabinet d'avocats / notariat / audit practice) | Claude Cowork | Done | P0 | 2026-04-18 | T-400, T-401, T-402 | docs/brand/BRAND-GUIDELINES.md + Obsidian mirror + CLAUDE.md sync | [2026-04-18] Issues #64 + #65. v1.1 overrule: no 'advocate's voice' framing. Commit c6f6624 pushed.
T-405 | Frontend | Build GlobalHeader server component + wire into layout.tsx, remove local page header | Claude Cowork | Done | P1 | 2026-04-17 | T-400 | src/components/GlobalHeader.tsx, src/app/[locale]/layout.tsx | [2026-04-17] Issues #53 + #54.
T-406 | Frontend | Build /account page with user profile + consents snapshot + billing history | Claude Cowork | Done | P1 | 2026-04-17 | T-001 | src/app/[locale]/account/page.tsx | [2026-04-17] Issue #55.
T-407 | Legal | Build delete-account flow — GDPR Art 17 right to erasure, 30-day soft-delete grace period | Claude Cowork | Done | P0 | 2026-04-17 | T-001, T-406 | src/app/[locale]/account/delete/page.tsx + /api/account/delete | [2026-04-17] Issue #56.
T-408 | Frontend | Visual polish on landing hero + login — Apple HIG motion, reduced-motion respected | Claude Cowork | Done | P2 | 2026-04-17 | T-401, T-403 | src/app/[locale]/page.tsx, src/app/[locale]/login/page.tsx | [2026-04-17] Issue #57.
T-409 | Pricing | Lock 5-tier pricing grid (T1 €15 → T5+/maison €35) + exit_only €25 + dispute €20 + préavis €5 + colocation rule | Claude Cowork | Done | P0 | 2026-04-17 | None | src/lib/stripe.ts + /pricing page + CLAUDE.md | [2026-04-17] Issues #34, #39, #43. FR-only launch. Per-tenant, couple=one, no meublé surcharge.
T-410 | Backend | Fix RLS silent failure on Stripe webhook writes — route /api/webhooks/stripe through admin client | Claude Cowork | Done | P0 | 2026-04-17 | T-001, T-003 | src/app/api/webhooks/stripe/route.ts + src/lib/supabase/admin.ts | [2026-04-17] Issues #44 + #51. Every supabase write now destructures { error }.
T-411 | Database | Migration 003 — add tax_country, tax_rate, tax_amount, tax_exclusive columns to payments table | Claude Cowork | Done | P0 | 2026-04-17 | T-001 | supabase/migrations/003_tax_columns.sql | [2026-04-17] Issue #38. Backs T-418 Stripe Tax + OSS flow.
T-412 | Backend | Evidence chain — persist sha256 + EXIF (camera/lens/timestamp/orientation) on photo upload, denorm inspection_id | Claude Cowork | Done | P0 | 2026-04-17 | T-002 | src/app/api/upload/route.ts + supabase/migrations | [2026-04-17] Issue #23. Geolocation deliberately skipped for GDPR minimisation. Commit 0240bec.
T-413 | Backend | Risk-scan v2 — /api/ai/scan with FR prompt, grille JSON, zod validation, retry Haiku→Haiku→Sonnet, €0.12 cost cap | Claude Cowork | Done | P0 | 2026-04-17 | T-001, T-412 | src/app/api/ai/scan/route.ts + src/lib/ai/prompts/scan-v2.ts | [2026-04-17] Issue #22 + #33.
T-414 | Backend | Dispute-letter v2 — /api/ai/dispute FR/EN split, tenant_rationale fence, Sonnet→Sonnet retry, €0.50 cap, disclaimer server-injected | Claude Cowork | In Progress | P0 | 2026-04-24 | T-413 | src/app/api/ai/dispute/route.ts + src/lib/ai/prompts/dispute-v2.ts | [2026-04-18] Issue #30. Typecheck blocked on sandbox — verify on Vercel preview.
T-415 | Mobile | Mobile scaffold — Capacitor 6 iOS+Android bundles + /api/mobile/upload-intent + /api/mobile/upload-commit | Claude Cowork | Done | P1 | 2026-04-17 | T-002, T-004 | capacitor.config.ts + ios/ + android/ + src/app/api/mobile/* | [2026-04-17] Issues #24, #49, #50.
T-416 | Infrastructure | Configure Brevo SMTP in Supabase Auth settings (replace default Supabase mailer) | Dr Mubashir | Done | P0 | 2026-04-17 | T-005 | Supabase Auth → SMTP provider | [2026-04-17] Issue #46. Quota widened for magic-link volume.
T-417 | Legal | Publish 6 legal docs as /legal/* routes with DRAFT banner (privacy, terms, refund, cookies, CGU, ML notice) FR+EN | Claude Cowork | Done | P0 | 2026-04-17 | None | src/app/[locale]/legal/* | [2026-04-17] Issue #17.
T-418 | Legal | Enable Stripe Tax + register OSS (guichet unique) with DGFiP — TVA 20% FR standard rate, OSS for non-FR EU B2C | Dr Mubashir | To Do | P0 | 2026-04-30 | T-411 | Stripe Tax enabled + OSS registration receipt | Issue #37. Required before first non-FR-EU invoice.
T-419 | Infrastructure | ECB daily refresh cron — EUR/GBP rate refresh for multi-currency totals | Claude Cowork | To Do | P1 | 2026-05-06 | T-001 | Supabase Edge Function or Vercel cron | Issue #27. Not blocking soft launch (FR-only).
T-420 | QA | T-103 core pipeline tests — payment → scan → report → email, dry run before soft launch | Claude Cowork | To Do | P0 | 2026-05-08 | T-020, T-414 | tests/pipelines/*.test.ts + dry-run report | Issue #26. Must pass before 11 May.
T-421 | Legal | Consents table + 4 UX touchpoints (signup, payment, scan, dispute) — GDPR Art 7 + ePrivacy | Claude Cowork | In Progress | P0 | 2026-04-25 | T-001, T-422, T-423 | supabase/migrations + src/components/consent/* + /api/consents | Issue #29. Blocked by #47 OAuth External + #48 Magic Link template.
T-422 | Infrastructure | Switch Google OAuth consent screen from Internal to External user type | Dr Mubashir | To Do | P0 | 2026-04-22 | None | Google Cloud Console → OAuth consent screen → External | Issue #47. Blocks T-421 signup path.
T-423 | Infrastructure | Edit Supabase Magic Link email template to use token_hash + type (new PKCE flow) | Dr Mubashir | To Do | P0 | 2026-04-22 | T-416 | Supabase Auth → Email templates → Magic Link | Issue #48. Blocks T-421 signup path.
T-424 | Agents | Set up Telegram push channel — BotFather token + chat_id + LaunchAgent integration | Dr Mubashir | In Progress | P1 | 2026-04-25 | None | ~/.paperclip-monitor.env + LaunchAgent plist | Issue #32.
T-425 | Mobile | App icons, splash screens, store listings (copy + screenshots ZH/AR/UR) for App Store + Play Store | Claude Cowork | To Do | P1 | 2026-05-20 | T-415 | ios/App/Assets.xcassets + android/app/src/main/res/* + store listing copy | Issue #31. After soft launch.
T-426 | Pipeline | Wire end-to-end pipeline Stripe → Supabase → R2 → Haiku scan → @react-pdf/renderer → R2 → Brevo email | Claude Cowork | To Do | P0 | 2026-05-08 | T-020, T-413, T-416 | src/app/api/webhooks/stripe/route.ts (extended) + /api/pipelines/* | Issue #25. Core revenue path. Must ship by 8 May dry run.
T-427 | Legal | Decide médiateur de la consommation (CMAP, SMP, Medicys) — mandatory per art. L612-1 Code conso | Dr Mubashir | To Do | P0 | 2026-04-25 | None | Signed adhésion + médiateur name/URL surfaced on /legal/* footer + CGV | Issue #15. Pre-launch regulatory gate.
T-428 | Backend | Align EDL condition taxonomy to French legal labels (bon/moyen/mauvais/très mauvais état) across grille + UI + report | Claude Cowork | To Do | P1 | 2026-04-30 | T-413 | src/lib/inspection/elements.ts + src/lib/ai/prompts/scan-v2.ts + report renderer | Issue #35. Removes EN/FR label drift before soft launch.
T-429 | Product | Post-launch: préavis letter add-on €5 with zone tendue lookup | Claude Cowork | To Do | P2 | 2026-06-15 | T-426 | src/app/[locale]/preavis/* + /api/ai/preavis + SKU preavis_letter | Issue #41. Post-11-May launch. SKU already in stripe.ts.
T-430 | Product | Post-launch: pre-exit self-check mode — 15-20 days before move-out, tenant self-audit against entry baseline | Claude Cowork | To Do | P2 | 2026-06-20 | T-426 | src/app/[locale]/pre-exit/* + /api/ai/pre-exit-checklist | Issue #42. Post-launch, unlocks exit-scan conversion path.

## Weekly Cadence
Day | Time | Activity | Who | Input | Output | Duration
Monday | 09:00 | CEO Agent weekly review run | CEO Agent (auto) | All open issues + status from Paperclip | Strategic priority list + risk flags on Telegram | ~5 min run
Monday | 09:30 | Dr Mubashir reviews CEO output + updates reste-à-faire | Dr Mubashir | CEO review + this Excel | Updated task statuses, new tasks if needed | 15 min
Mon-Thu | Working hours | Execution: Claude Cowork sessions on P0/P1 tasks | Dr Mubashir + Claude | Reste-à-faire priority order | Code commits, configs, content | As available
Wednesday | On demand | CTO review run (if architecture decision needed) | Dr Mubashir triggers | Specific question or PR to review | Technical recommendation on Telegram | ~3 min run
Friday | 17:00 | Weekly reste-à-faire update + git push | Dr Mubashir + Claude | This Excel + git status | Updated Excel, clean git history | 20 min
Friday | 17:30 | Telegram digest: week summary (automated) | Monitor script | Paperclip DB state | Agent run stats + issue counts | Auto
End of month | Any | Monthly financial review vs. projections | Dr Mubashir | Expenses + 04-Financial projections | Variance report | 1 hour

## SQL Commands
PAPERCLIP RECONFIGURATION SQL — Run these in order
Step | SQL Command
1. Cancel all queued wakeups | UPDATE agent_wakeup_requests SET status = 'cancelled' WHERE status = 'queued';
2. Pause all Ollama agents | UPDATE agents SET paused_at = NOW(), pause_reason = 'option_c_governance_only' WHERE adapter_type = 'codex_local';
3. Keep CEO + CTO active | UPDATE agents SET paused_at = NULL, pause_reason = NULL WHERE adapter_type = 'claude_local';
4. Reset CTO budget (fresh start) | UPDATE agents SET spent_monthly_cents = 0 WHERE name = 'CTO';
5. Close stale CTO issues | UPDATE issues SET status = 'done' WHERE assignee_agent_id = (SELECT id FROM agents WHERE name = 'CTO') AND status IN ('backlog') AND title LIKE '%Hire%';
6. Close stale CTO directive | UPDATE issues SET status = 'done' WHERE assignee_agent_id = (SELECT id FROM agents WHERE name = 'CTO') AND title LIKE '%OPERATING DIRECTIVE%';
7. Archive unassigned backlog | UPDATE issues SET status = 'done' WHERE assignee_agent_id IS NULL AND status = 'backlog';
VERIFICATION QUERY
Check final state | SELECT name, status, adapter_type, paused_at IS NOT NULL as paused, budget_monthly_cents, spent_monthly_cents FROM agents ORDER BY name;
COMBINED ONE-LINER (copy-paste into Terminal)
Full reconfiguration | PGPASSWORD=paperclip /opt/homebrew/Cellar/libpq/18.3/bin/psql -h localhost -p 54329 -U paperclip -d paperclip -c " UPDATE agent_wakeup_requests SET status = 'cancelled' WHERE status = 'queued'; UPDATE agents SET paused_at = NOW(), pause_reason = 'option_c_governance_only' WHERE adapter_type = 'codex_local'; UPDATE agents SET paused_at = NULL, pause_reason = NULL WHERE adapter_type = 'claude_local'; UPDATE agents SET spent_monthly_cents = 0 WHERE name = 'CTO'; UPDATE issues SET status = 'done' WHERE assignee_agent_id = (SELECT id FROM agents WHERE name = 'CTO') AND status = 'backlog'; UPDATE issues SET status = 'done' WHERE assignee_agent_id IS NULL AND status = 'backlog'; SELECT name, status, adapter_type, CASE WHEN paused_at IS NOT NULL THEN 'PAUSED' ELSE 'ACTIVE' END as state, budget_monthly_cents/100 as budget_usd, spent_monthly_cents/100 as spent_usd FROM agents ORDER BY name; "

## Paperclip Status
PAPERCLIP STATUS — RETIRED 2026-04-17 (dashboard-only)
Issue #18 closed: all 10 agents paused, 14 issues closed. governance-sync LaunchAgent runs every 30 min.
Execution runs through Claude Cowork sessions; no agent fleet.
Agent | Adapter | Model | State | Budget | Spent | Retirement note
CEO | codex_local | gpt-4o-mini | PAUSED | $15 | $4.06 | Chat-only; never executed tool calls.
CTO | codex_local | gpt-4o-mini | PAUSED | $20 | $13.78 | Chat-only; never executed tool calls.
Head of Finance | codex_local | gemma4:e4b | PAUSED | $5 | $0.00 | Ollama adapter failed (0% success).
Head of Governance | codex_local | gemma4:e4b | PAUSED | $5 | $0.00 | Ollama adapter failed (0% success).
Head of HR | codex_local | gemma4:e4b | PAUSED | $5 | $0.00 | Ollama adapter failed (0% success).
Head of Marketing | codex_local | gemma4:e4b | PAUSED | $5 | $0.00 | Ollama adapter failed (0% success).
Head of Product | codex_local | gemma4:e4b | PAUSED | $5 | $0.00 | Ollama adapter failed (0% success).
Senior Android Developer | codex_local | gemma4:e4b | PAUSED | $5 | $0.00 | Error state before retirement.
Senior Web Developer | codex_local | gemma4:e4b | PAUSED | $5 | $0.00 | Ollama adapter failed (0% success).
Senior iOS Developer | codex_local | gemma4:e4b | PAUSED | $5 | $0.00 | Error state before retirement.
ISSUE SUMMARY (final, frozen 2026-04-17)
done | 42
closed at retirement | 14
obsolete (T-084..T-316) | 22
REPLACEMENT
Execution: Claude Cowork session cadence (see Weekly Cadence tab).
Monitoring: governance-sync LaunchAgent every 30 min + Telegram digest (T-424 in progress).

## Run History
RUN HISTORY (Last 24h) — 2026-04-17 19:19
Agent | Status | Duration | Error | Started | Finished
CEO | succeeded | 0m |  | 2026-04-17 12:12:52 | 2026-04-17 12:13:12
CEO | succeeded | 0m |  | 2026-04-17 12:07:22 | 2026-04-17 12:07:30
CEO | succeeded | 0m |  | 2026-04-17 12:01:52 | 2026-04-17 12:02:05
CEO | succeeded | 0m |  | 2026-04-17 11:56:22 | 2026-04-17 11:56:37
CEO | succeeded | 0m |  | 2026-04-17 11:50:52 | 2026-04-17 11:51:19
CEO | succeeded | 0m |  | 2026-04-17 11:45:22 | 2026-04-17 11:45:29
CEO | succeeded | 0m |  | 2026-04-17 11:39:52 | 2026-04-17 11:40:04
CEO | succeeded | 0m |  | 2026-04-17 11:34:22 | 2026-04-17 11:34:41
CEO | succeeded | 0m |  | 2026-04-17 11:28:52 | 2026-04-17 11:29:02
CEO | succeeded | 0m |  | 2026-04-17 11:23:22 | 2026-04-17 11:23:28
CEO | succeeded | 0m |  | 2026-04-17 11:17:52 | 2026-04-17 11:18:03
CEO | succeeded | 0m |  | 2026-04-17 11:12:14 | 2026-04-17 11:12:43
CEO | succeeded | 0m |  | 2026-04-17 11:08:52 | 2026-04-17 11:08:58
CTO | succeeded | 0m |  | 2026-04-17 11:03:30 | 2026-04-17 11:03:37
CEO | succeeded | 0m |  | 2026-04-17 11:03:24 | 2026-04-17 11:03:35
CEO | succeeded | 0m |  | 2026-04-17 11:01:52 | 2026-04-17 11:02:02
CTO | succeeded | 0m |  | 2026-04-17 10:56:27 | 2026-04-17 10:56:35
CEO | succeeded | 0m |  | 2026-04-17 10:56:27 | 2026-04-17 10:56:35
CEO | succeeded | 0m |  | 2026-04-17 10:53:52 | 2026-04-17 10:54:01
CEO | succeeded | 0m |  | 2026-04-17 10:48:22 | 2026-04-17 10:48:37
CEO | succeeded | 0m |  | 2026-04-17 10:42:52 | 2026-04-17 10:43:02
CEO | succeeded | 0m |  | 2026-04-17 10:37:22 | 2026-04-17 10:37:29
CEO | succeeded | 0m |  | 2026-04-17 10:31:52 | 2026-04-17 10:32:02
CEO | succeeded | 0m |  | 2026-04-17 10:26:22 | 2026-04-17 10:26:28
CEO | succeeded | 0m |  | 2026-04-17 10:20:52 | 2026-04-17 10:21:17
CEO | succeeded | 0m |  | 2026-04-17 10:15:22 | 2026-04-17 10:15:29
CEO | succeeded | 0m |  | 2026-04-17 10:09:52 | 2026-04-17 10:10:05
CEO | succeeded | 0m |  | 2026-04-17 10:04:22 | 2026-04-17 10:04:38
CEO | succeeded | 0m |  | 2026-04-17 09:58:52 | 2026-04-17 09:59:08
CEO | succeeded | 0m |  | 2026-04-17 09:53:22 | 2026-04-17 09:53:29
CEO | succeeded | 0m |  | 2026-04-17 09:47:52 | 2026-04-17 09:47:58
CEO | succeeded | 0m |  | 2026-04-17 09:42:22 | 2026-04-17 09:42:27
CEO | succeeded | 0m |  | 2026-04-17 09:36:52 | 2026-04-17 09:37:00
CEO | succeeded | 8m |  | 2026-04-17 09:23:27 | 2026-04-17 09:31:27
CEO | timed_out | 17m | Timed out after 900s | 2026-04-17 08:49:10 | 2026-04-17 09:06:32
CEO | timed_out | 16m | Timed out after 900s | 2026-04-17 08:16:50 | 2026-04-17 08:33:02
CEO | succeeded | 0m |  | 2026-04-17 08:11:20 | 2026-04-17 08:11:28
CEO | succeeded | 0m |  | 2026-04-17 08:05:50 | 2026-04-17 08:06:12
CEO | succeeded | 0m |  | 2026-04-17 07:59:50 | 2026-04-17 08:00:20
CEO | succeeded | 0m |  | 2026-04-17 07:54:20 | 2026-04-17 07:54:45
CEO | timed_out | 20m | Timed out after 900s | 2026-04-17 07:33:28 | 2026-04-17 07:54:20
CEO | timed_out | 16m | Timed out after 900s | 2026-04-17 07:16:37 | 2026-04-17 07:33:28
CEO | timed_out | 17m | Timed out after 900s | 2026-04-17 06:58:44 | 2026-04-17 07:16:37
CEO | timed_out | 28m | Timed out after 900s | 2026-04-17 06:30:30 | 2026-04-17 06:58:44
CEO | timed_out | 16m | Timed out after 900s | 2026-04-17 06:13:51 | 2026-04-17 06:30:30
CEO | timed_out | 17m | Timed out after 900s | 2026-04-17 05:40:44 | 2026-04-17 05:57:55
CEO | timed_out | 15m | Timed out after 900s | 2026-04-17 05:13:44 | 2026-04-17 05:28:51
CEO | timed_out | 30m | Timed out after 900s | 2026-04-17 04:26:04 | 2026-04-17 04:56:33
CEO | timed_out | 16m | Timed out after 900s | 2026-04-17 03:53:51 | 2026-04-17 04:10:45
CEO | timed_out | 15m | Timed out after 900s | 2026-04-17 03:38:43 | 2026-04-17 03:53:51
CEO | timed_out | 19m | Timed out after 900s | 2026-04-17 03:11:18 | 2026-04-17 03:30:37
CEO | timed_out | 16m | Timed out after 900s | 2026-04-17 02:37:43 | 2026-04-17 02:54:24
CEO | timed_out | 17m | Timed out after 900s | 2026-04-17 02:10:00 | 2026-04-17 02:27:59
CEO | timed_out | 29m | Timed out after 900s | 2026-04-17 01:25:01 | 2026-04-17 01:54:16
CEO | timed_out | 15m | Timed out after 900s | 2026-04-17 01:09:55 | 2026-04-17 01:25:01
CEO | timed_out | 20m | Timed out after 900s | 2026-04-17 00:33:15 | 2026-04-17 00:53:19
CEO | timed_out | 24m | Timed out after 900s | 2026-04-16 23:51:44 | 2026-04-17 00:16:23
CEO | timed_out | 28m | Timed out after 900s | 2026-04-16 23:23:05 | 2026-04-16 23:51:44
CEO | timed_out | 16m | Timed out after 900s | 2026-04-16 23:06:41 | 2026-04-16 23:23:05
CEO | timed_out | 26m | Timed out after 900s | 2026-04-16 22:24:28 | 2026-04-16 22:50:39
CEO | timed_out | 18m | Timed out after 900s | 2026-04-16 22:06:27 | 2026-04-16 22:24:28
CEO | timed_out | 31m | Timed out after 900s | 2026-04-16 21:18:50 | 2026-04-16 21:50:20
CEO | timed_out | 16m | Timed out after 900s | 2026-04-16 21:02:10 | 2026-04-16 21:18:50
CEO | timed_out | 27m | Timed out after 900s | 2026-04-16 20:19:12 | 2026-04-16 20:46:53
CEO | timed_out | 15m | Timed out after 900s | 2026-04-16 19:47:03 | 2026-04-16 20:02:06
CEO | succeeded | 0m |  | 2026-04-16 19:30:43 | 2026-04-16 19:30:51