## Priority Summary
TENU.WORLD — TASK TRACKER
Regenerated 2026-05-08 from TASKS.md. Master = TASKS.md. Do not edit xlsx directly.
BY STATUS
Status | Count
Open | 60
In Progress | 5
Done | 39
Dropped | 0
BY PRIORITY (open only)
Priority | Count | Note
P0 Blocker | 49 | Must clear before soft launch 11 May 2026
P1 Important | 11 | Nice to have at launch, not blocking
P2 Post-launch | 5 | After 11 May
BY OWNER (open only)
Owner | Count
MH | 41
CC | 24
NEXT 7 DAYS (open + due within 7 days)
Due | Owner | Priority | Title
2026-04-20 | MH | P0 Blocker | Apple Developer Program enrollment for Global Apex NET SAS, EUR 99/year
2026-04-23 | CC | P0 Blocker | End-to-end pipeline wiring Stripe webhook → Supabase → R2 → Haiku → @react-pdf/renderer → R2 → Brevo
2026-05-04 | CC | P0 Blocker | Update store-listing copy + welcome email + landing page to reflect web-first launch + native binaries follow
2026-05-04 | MH | P0 Blocker | Personalise + send the UK solicitor brief (review draft, fill recipient name + firm, send by email)
2026-05-04 | MH | P0 Blocker | Check D-U-N-S number for Global Apex NET SAS at dnb.com/duns-number-lookup
2026-05-04 | MH | P0 Blocker | Email UK housing-law solicitor for fixed-fee TDS/DPS template review, GBP 500-1500 budget
2026-05-04 | MH | P0 Blocker | Email French avocat droit immobilier for fixed-fee legal v1.0 review
2026-05-04 | MH | P0 Blocker | Google Play Console developer account, USD 25 one-time
2026-05-04 | MH | P0 Blocker | Confirm SAS legal name + siège exactly match Apple + Play enrolment forms
2026-05-04 | MH | P0 Blocker | Audit hidden env vars
2026-05-04 | MH | P0 Blocker | Lock down NEXT_PUBLIC_GOOGLE_MAPS_API_KEY at source
2026-05-04 | MH | P0 Blocker | Tick Sensitive on every remaining non-public secret in Vercel env var list
2026-05-04 | CC | P0 Blocker | Stripe Checkout in-app web view with return-URL deep link back to app
2026-05-04 | CC | P0 Blocker | Signed iOS production binary uploaded to App Store Connect
2026-05-04 | CC | P0 Blocker | Signed Android app bundle uploaded to Play Console production track
2026-05-04 | CC | P1 Important | Move native-build MH lines (build:mobile, cap add, cap sync, Xcode, Android Studio) into the Native Build Bridge section dated 18-25 May
2026-05-04 | MH | P1 Important | Install scheduled-push v2
2026-05-05 | CC | P0 Blocker | Native Build Bridge plan
2026-05-05 | MH | P0 Blocker | Google Workspace subscription on `tenu.world`
2026-05-05 | MH | P0 Blocker | Create new Cloud project `tenu-production` signed in as `ops@tenu.world` at console.cloud.google.com
2026-05-05 | MH | P0 Blocker | Verify `tenu.world` domain ownership via Search Console TXT record
2026-05-05 | MH | P0 Blocker | OAuth consent screen → User Type: External → App name "Tenu" → support email `support@tenu.world` → developer contact `dpo@tenu.world` → scopes: email, profile, openid only
2026-05-05 | MH | P0 Blocker | Create OAuth 2.0 Client ID (Web application) → authorized redirect URI = Supabase callback (`https://<project-ref>.supabase.co/auth/v1/callback`) → save client_id + client_secret into 1Password, NOT to disk
2026-05-05 | MH | P0 Blocker | Paste new client_id + client_secret into Supabase dashboard → Authentication → Providers → Google → Save
2026-05-05 | MH | P0 Blocker | Before 11 May
2026-05-05 | MH | P0 Blocker | Decide Apple IAP stance
2026-05-05 | CC | P0 Blocker | Magic-link auth working inside app
2026-05-05 | MH | P0 Blocker | dpo@tenu.world mailbox live with auto-acknowledge
2026-05-05 | MH | P0 Blocker | 512x512 production logo finalised, favicon set, OG image
2026-05-06 | MH | P0 Blocker | Smoke-test Google login end-to-end on tenu.world production + localhost
2026-05-06 | MH | P0 Blocker | Delete `05-Legal-Compliance/client_secret_1016793771503-bnq65154rootrva2e81kh1jicoks7hss.apps.googleusercontent.com.json` AND the ` (1).json` duplicate from disk. `rm` only
2026-05-06 | MH | P0 Blocker | Shut down old `gen-lang-client-0896170717` Cloud project (Cloud Console → Settings → Shut down)
2026-05-06 | MH | P0 Blocker | Sign DPAs with Supabase, Cloudflare, Stripe, Vercel, Brevo, Anthropic
2026-05-06 | MH | P0 Blocker | Review store listing copy in Notion/file, approve or edit
2026-05-06 | MH | P0 Blocker | F&F invite list
2026-05-07 | MH | P0 Blocker | French avocat sign-off on legal v1.0, strip DRAFT banners
2026-05-07 | MH | P0 Blocker | UK solicitor sign-off on TDS/DPS template
2026-05-07 | CC | P1 Important | Push notifications APNs + FCM for risk-scan complete + letter ready
2026-05-08 | CC | P0 Blocker | 6 iOS screenshots at 6.9 inch + 4 Play screenshots at 16:9
2026-05-08 | MH | P1 Important | Recover Brevo account access
2026-05-09 | MH | P0 Blocker | Suivi avocat·e
2026-05-09 | MH | P0 Blocker | Médiateur de la consommation
2026-05-09 | CC | P0 Blocker | Bug sweep on inspection UI
2026-05-10 | CC | P0 Blocker | F&F install test on 2 real devices each (iPhone + Android)
2026-05-11 | MH | P0 Blocker | Invite F&F list on 11 May 09:00 Paris
2026-05-12 | MH | P0 Blocker | Run `npm run build:mobile` on Mac to produce out/ static export
2026-05-12 | MH | P0 Blocker | Run `npx cap add ios` on Mac, then merge mobile/ios-Info.plist.snippet.xml entries into ios/App/App/Info.plist
2026-05-12 | MH | P0 Blocker | Run `npx cap add android` on Mac, then merge mobile/android-manifest.snippet.xml + drop network_security_config.xml under res/xml/
2026-05-12 | MH | P0 Blocker | Monitor first 24h, triage, log issues, not fix
2026-05-13 | MH | P0 Blocker | Run `npx capacitor-assets generate --iconBackgroundColor "#0B1F3A" --iconBackgroundColorDark "#0B1F3A" --splashBackgroundColor "#F4F1EA" --splashBackgroundColorDark "#0B1F3A"` after cap add
2026-05-13 | MH | P0 Blocker | Run `npx cap sync` to wire build:mobile output into native projects
2026-05-14 | MH | P0 Blocker | Open Xcode (`npx cap open ios`), set Team ID + Bundle world.tenu.app + capabilities (Camera, Push, Associated Domains for tenu.world), run on simulator + physical iPhone
2026-05-14 | MH | P0 Blocker | Open Android Studio (`npx cap open android`), set release keystore SHA-256 in mobile/.well-known/assetlinks.json placeholder, run on emulator + physical device
2026-05-15 | CC | P1 Important | Wire e2e env
2026-05-15 | CC | P1 Important | Lawyer formal sign-off letter (FR avocat + UK solicitor)

## Open
ID | Section | Status | Owner | Priority | Due | Title | Note
T-001 | DECISION 2026-05-03 — Launch path: Option B (web-only on 11 May) | In Progress | CC | P0 Blocker | 2026-05-04 | Update store-listing copy + welcome email + landing page to reflect web-first launch + native binaries follow | opened 2026-05-03.
T-002 | DECISION 2026-05-03 — Launch path: Option B (web-only on 11 May) | Open | CC | P0 Blocker | 2026-05-05 | Native Build Bridge plan | write docs/12-Native-Build-Bridge-2026-05-12.md mapping the 11-25 May path: cap add ios + cap add android dependencies, Xcode + Android Studio prerequisites, TestFlight + Play internal track submission, screenshots backlog, App Store reviewer notes refresh — opened 2026-05-03.
T-003 | DECISION 2026-05-03 — Launch path: Option B (web-only on 11 May) | Open | CC | P1 Important | 2026-05-04 | Move native-build MH lines (build:mobile, cap add, cap sync, Xcode, Android Studio) into the Native Build Bridge section dated 18-25 May | keep their content verbatim, only re-section + re-date so the launch checklist stops bleeding red on items that were never blocking 11 May web-only — opened 2026-05-03.
T-004 | LEGAL — fixed-fee review briefs (CC drafts ready for MH to send, opened 2026-05-03) | Open | MH | P0 Blocker | 2026-05-09 | Suivi avocat·e | relance polie si pas de réponse à J+2 — opened 2026-05-07. Critical path pour décision launch-vs-slip 11 May ; bloque CGU §11 médiateur, mentions légales §médiation, et la levée des bannières DRAFT.
T-005 | LEGAL — fixed-fee review briefs (CC drafts ready for MH to send, opened 2026-05-03) | Open | MH | P0 Blocker | 2026-05-04 | Personalise + send the UK solicitor brief (review draft, fill recipient name + firm, send by email) | depends on CC line above.
T-006 | THIS WEEKEND (17-20 Apr) | In Progress | MH | P1 Important | 2026-05-04 | Install scheduled-push v2 | copy scripts/scheduled-tasks/tenu-daily-push.md into ~/Documents/Claude/Scheduled/tenu-daily-push/SKILL.md and drop BREVO_API_KEY into .secrets/brevo.env — re-dated 2026-05-03. CC fixed all 6 hardcoded paths in SKILL.md from `/Users/mmh/Documents/Claude/Projects/Tenu.World/` to `/Users/mmh/Code/Tenu.World/` (root cause of today's 09:04 diagnostic log). Bumped to v2.1. brevo.env.example header path also corrected. SKILL.md installed at ~/Documents/Claude/Scheduled/tenu-daily-push/SKILL.md. .secrets/brevo.env file created but currently holds CC's placeholder text (51 bytes, "xkeysib-PASTE_THE_REAL_KEY_VALUE_HERE"). MH must pull real BREVO_API_KEY from Vercel env panel and overwrite. After overwrite, remove the [>] marker and close [x].
T-007 | THIS WEEKEND (17-20 Apr) | Open | MH | P1 Important | 2026-05-08 | Recover Brevo account access | can't log in to dashboard as of 2026-05-03. Try password reset at app.brevo.com/account/login → mubashirr@gmail.com. If 2FA is the blocker, contact Brevo support (help.brevo.com) for identity-verified MFA reset. Search Downloads folder for any "brevo" or "recovery" file from original signup. Needed before F&F cohort outcome data starts coming in mid-May (template tuning + bounce monitoring)
T-008 | THIS WEEKEND (17-20 Apr) | Open | MH | P0 Blocker | 2026-05-04 | Check D-U-N-S number for Global Apex NET SAS at dnb.com/duns-number-lookup
T-009 | THIS WEEKEND (17-20 Apr) | Open | MH | P0 Blocker | 2026-05-04 | Email UK housing-law solicitor for fixed-fee TDS/DPS template review, GBP 500-1500 budget
T-010 | THIS WEEKEND (17-20 Apr) | Open | MH | P0 Blocker | 2026-05-04 | Email French avocat droit immobilier for fixed-fee legal v1.0 review
T-011 | THIS WEEKEND (17-20 Apr) | In Progress | MH | P0 Blocker | 2026-04-20 | Apple Developer Program enrollment for Global Apex NET SAS, EUR 99/year | submitted 2026-05-03, documents sent to Apple, awaiting verification (per Dr Mubashir). Apple identity check typically 2-5 business days; D-U-N-S verification gates the review. Track unblocking of Xcode signing / TestFlight upload off this line.
T-012 | THIS WEEKEND (17-20 Apr) | Open | MH | P0 Blocker | 2026-05-04 | Google Play Console developer account, USD 25 one-time
T-013 | THIS WEEKEND (17-20 Apr) | Open | MH | P0 Blocker | 2026-05-04 | Confirm SAS legal name + siège exactly match Apple + Play enrolment forms
T-014 | THIS WEEKEND (17-20 Apr) | Open | MH | P0 Blocker | 2026-05-05 | Google Workspace subscription on `tenu.world` | create `ops@tenu.world` (owner) + `support@tenu.world` + `dpo@tenu.world` (aliases acceptable)
T-015 | THIS WEEKEND (17-20 Apr) | Open | MH | P0 Blocker | 2026-05-05 | Create new Cloud project `tenu-production` signed in as `ops@tenu.world` at console.cloud.google.com
T-016 | THIS WEEKEND (17-20 Apr) | Open | MH | P0 Blocker | 2026-05-05 | Verify `tenu.world` domain ownership via Search Console TXT record
T-017 | THIS WEEKEND (17-20 Apr) | Open | MH | P0 Blocker | 2026-05-05 | OAuth consent screen → User Type: External → App name "Tenu" → support email `support@tenu.world` → developer contact `dpo@tenu.world` → scopes: email, profile, openid only
T-018 | THIS WEEKEND (17-20 Apr) | Open | MH | P0 Blocker | 2026-05-05 | Create OAuth 2.0 Client ID (Web application) → authorized redirect URI = Supabase callback (`https://<project-ref>.supabase.co/auth/v1/callback`) → save client_id + client_secret into 1Password, NOT to disk
T-019 | THIS WEEKEND (17-20 Apr) | Open | MH | P0 Blocker | 2026-05-05 | Paste new client_id + client_secret into Supabase dashboard → Authentication → Providers → Google → Save
T-020 | THIS WEEKEND (17-20 Apr) | Open | MH | P0 Blocker | 2026-05-06 | Smoke-test Google login end-to-end on tenu.world production + localhost | expect no 403 org_internal, consent screen shows "Tenu" with `support@tenu.world`
T-021 | THIS WEEKEND (17-20 Apr) | Open | MH | P0 Blocker | 2026-05-06 | Delete `05-Legal-Compliance/client_secret_1016793771503-bnq65154rootrva2e81kh1jicoks7hss.apps.googleusercontent.com.json` AND the ` (1).json` duplicate from disk. `rm` only | do not archive, the secret is burned
T-022 | THIS WEEKEND (17-20 Apr) | Open | MH | P0 Blocker | 2026-05-06 | Shut down old `gen-lang-client-0896170717` Cloud project (Cloud Console → Settings → Shut down) | revokes the leaked secret at source even if a copy is still cached somewhere
T-023 | THIS WEEKEND (17-20 Apr) | Open | MH | P0 Blocker | 2026-05-05 | Before 11 May | publish OAuth consent screen Testing → Production (requires domain verified + privacy URL + terms URL live at tenu.world/legal/privacy + /legal/terms)
T-024 | THIS WEEKEND (17-20 Apr) | Open | MH | P0 Blocker | 2026-05-04 | Audit hidden env vars | scroll full Vercel env var list below the fold, confirm ANTHROPIC_API_KEY + BREVO_API_KEY + TELEGRAM_BOT_TOKEN + any other secret either shows Need To Rotate (rotate it) or was created Sensitive from day one (leave alone). If any non-public secret is unflagged and NOT marked Sensitive, treat as exposed and rotate
T-025 | THIS WEEKEND (17-20 Apr) | Open | MH | P0 Blocker | 2026-05-04 | Lock down NEXT_PUBLIC_GOOGLE_MAPS_API_KEY at source | Google Cloud Console → APIs & Services → Credentials → restrict to HTTP referrers `*.tenu.world` + `localhost:*` + enable only Maps JavaScript + Places API. Public by design, not flagged by Vercel, but unrestricted = scraping risk against Global Apex billing
T-026 | THIS WEEKEND (17-20 Apr) | Open | MH | P0 Blocker | 2026-05-04 | Tick Sensitive on every remaining non-public secret in Vercel env var list | hardening pass, single biggest structural lesson from this incident. Anything that isn't a NEXT_PUBLIC_* or a non-secret identifier (R2_ACCOUNT_ID, R2_BUCKET_NAME) should be Sensitive
T-027 | WEEK 1 (20-24 Apr) — pipeline + native scaffold | In Progress | CC | P0 Blocker | 2026-04-23 | End-to-end pipeline wiring Stripe webhook → Supabase → R2 → Haiku → @react-pdf/renderer → R2 → Brevo | partially wired 2026-04-18: Stripe webhook → Supabase chain live (src/app/api/webhooks/stripe/route.ts, commit ce748ec, admin client bypasses RLS). Photos up through R2, scan via /api/ai/scan (Haiku) and dispute via /api/ai/dispute (Sonnet). MISSING: @react-pdf/renderer PDF generation step (only present in features/scan marketing page, not pipeline), Brevo transactional email leg (zero references in src/). Split into two new tasks below.
T-028 | WEEK 1 (20-24 Apr) — pipeline + native scaffold | Open | MH | P0 Blocker | 2026-05-12 | Run `npm run build:mobile` on Mac to produce out/ static export
T-029 | WEEK 1 (20-24 Apr) — pipeline + native scaffold | Open | MH | P0 Blocker | 2026-05-12 | Run `npx cap add ios` on Mac, then merge mobile/ios-Info.plist.snippet.xml entries into ios/App/App/Info.plist
T-030 | WEEK 1 (20-24 Apr) — pipeline + native scaffold | Open | MH | P0 Blocker | 2026-05-12 | Run `npx cap add android` on Mac, then merge mobile/android-manifest.snippet.xml + drop network_security_config.xml under res/xml/
T-031 | WEEK 1 (20-24 Apr) — pipeline + native scaffold | Open | MH | P0 Blocker | 2026-05-13 | Run `npx capacitor-assets generate --iconBackgroundColor "#0B1F3A" --iconBackgroundColorDark "#0B1F3A" --splashBackgroundColor "#F4F1EA" --splashBackgroundColorDark "#0B1F3A"` after cap add
T-032 | WEEK 1 (20-24 Apr) — pipeline + native scaffold | Open | MH | P0 Blocker | 2026-05-13 | Run `npx cap sync` to wire build:mobile output into native projects
T-033 | WEEK 1 (20-24 Apr) — pipeline + native scaffold | Open | MH | P0 Blocker | 2026-05-14 | Open Xcode (`npx cap open ios`), set Team ID + Bundle world.tenu.app + capabilities (Camera, Push, Associated Domains for tenu.world), run on simulator + physical iPhone
T-034 | WEEK 1 (20-24 Apr) — pipeline + native scaffold | Open | MH | P0 Blocker | 2026-05-14 | Open Android Studio (`npx cap open android`), set release keystore SHA-256 in mobile/.well-known/assetlinks.json placeholder, run on emulator + physical device
T-035 | WEEK 1 (20-24 Apr) — pipeline + native scaffold | Open | CC | P1 Important |  | Android ↔ iOS native-chrome parity audit (splash, status bar, safe-area, fonts, haptics, hardware back, keyboard) | DEFERRED until MH completes `npx cap add ios`/`add android` + `cap sync` and both simulators boot a real `out/` bundle. Audit brief drafted 2026-04-19 (Dr Mubashir provided checkpoints a–l + parity checks 1–9). Cannot execute on empty native shells. Re-open this line once cap-add work lands.
T-036 | WEEK 1 (20-24 Apr) — pipeline + native scaffold | Open | MH | P0 Blocker | 2026-05-06 | Sign DPAs with Supabase, Cloudflare, Stripe, Vercel, Brevo, Anthropic
T-037 | OOO BRIDGE (27-30 Apr) | Open | CC | P0 Blocker | 2026-05-08 | 6 iOS screenshots at 6.9 inch + 4 Play screenshots at 16:9
T-038 | OOO BRIDGE (27-30 Apr) | Open | MH | P0 Blocker | 2026-05-06 | Review store listing copy in Notion/file, approve or edit | re-dated 2026-05-03: depends on CC web-only listing revision (line in DECISION 2026-05-03 section).
T-039 | OOO BRIDGE (27-30 Apr) | Open | MH | P0 Blocker | 2026-05-05 | Decide Apple IAP stance | physical service argument documented — re-dated 2026-05-03: needs to land before App Store reviewer notes lock.
T-040 | WEEK 2 (4-7 May + 8 May bank holiday) — submit + pray | Open | CC | P0 Blocker | 2026-05-04 | Stripe Checkout in-app web view with return-URL deep link back to app
T-041 | WEEK 2 (4-7 May + 8 May bank holiday) — submit + pray | Open | CC | P0 Blocker | 2026-05-05 | Magic-link auth working inside app | email link opens app, session persists
T-042 | WEEK 2 (4-7 May + 8 May bank holiday) — submit + pray | Open | CC | P1 Important | 2026-05-07 | Push notifications APNs + FCM for risk-scan complete + letter ready
T-043 | WEEK 2 (4-7 May + 8 May bank holiday) — submit + pray | Open | CC | P0 Blocker | 2026-05-04 | Signed iOS production binary uploaded to App Store Connect
T-044 | WEEK 2 (4-7 May + 8 May bank holiday) — submit + pray | Open | CC | P0 Blocker | 2026-05-04 | Signed Android app bundle uploaded to Play Console production track
T-045 | WEEK 2 (4-7 May + 8 May bank holiday) — submit + pray | In Progress | MH | P0 Blocker | 2026-05-09 | Médiateur de la consommation | comparer MEDICYS vs CM2C (frais d'adhésion, délai de saisine, périmètre B2C numérique), choisir, signer, publier le nom dans CGU §11 + remboursement §6 + mentions légales §médiation — opened 2026-05-07: shortlist réduite à MEDICYS + CM2C, à arbitrer cette semaine. Obligation L612-1 Code de la conso pour activité B2C en ligne, blocage de la mise en service tant que le médiateur n'est pas adhéré.
T-046 | WEEK 2 (4-7 May + 8 May bank holiday) — submit + pray | Open | MH | P0 Blocker | 2026-05-07 | French avocat sign-off on legal v1.0, strip DRAFT banners
T-047 | WEEK 2 (4-7 May + 8 May bank holiday) — submit + pray | Open | MH | P0 Blocker | 2026-05-07 | UK solicitor sign-off on TDS/DPS template
T-048 | WEEK 2 (4-7 May + 8 May bank holiday) — submit + pray | Open | MH | P0 Blocker | 2026-05-05 | dpo@tenu.world mailbox live with auto-acknowledge
T-049 | WEEK 2 (4-7 May + 8 May bank holiday) — submit + pray | Open | MH | P0 Blocker | 2026-05-06 | F&F invite list | 8 names, email, jurisdiction, case type
T-050 | WEEK 2 (4-7 May + 8 May bank holiday) — submit + pray | Open | MH | P0 Blocker | 2026-05-05 | 512x512 production logo finalised, favicon set, OG image
T-051 | LAUNCH WEEK (8-11 May) | Open | CC | P0 Blocker | 2026-05-09 | Bug sweep on inspection UI | camera retries, upload resume, offline queue
T-052 | LAUNCH WEEK (8-11 May) | Open | CC | P0 Blocker | 2026-05-10 | F&F install test on 2 real devices each (iPhone + Android)
T-053 | LAUNCH WEEK (8-11 May) | Open | MH | P0 Blocker | 2026-05-11 | Invite F&F list on 11 May 09:00 Paris
T-054 | LAUNCH WEEK (8-11 May) | Open | MH | P0 Blocker | 2026-05-12 | Monitor first 24h, triage, log issues, not fix
T-055 | POST-LAUNCH (12-31 May) | Open | CC | P2 Post-launch |  | Full T-103 suite | 24 unit + 10 E2E + 5 canaries + 20 evals + OWASP ZAP baseline
T-056 | POST-LAUNCH (12-31 May) | Open | CC | P2 Post-launch |  | 14-day outcome survey cron | Brevo trigger + Supabase write-back
T-057 | POST-LAUNCH (12-31 May) | Open | CC | P2 Post-launch |  | Additional UI locales | ar, zh, hi, ur, ja, es, it, uk, pt, ko staged rollout
T-058 | POST-LAUNCH (12-31 May) | Open | CC | P1 Important |  | i18n audit phase 2 | inspection/new/page.tsx (715 lines, FR-hardcoded client component): extract all string literals into a `COPY: Record<Locale, InspectionCopy>` dict; room labels (Chambre, Séjour…), step labels, field labels, error messages
T-059 | POST-LAUNCH (12-31 May) | Open | CC | P2 Post-launch |  | App Store + Play production updates with post-launch fixes
T-060 | POST-LAUNCH (12-31 May) | Open | CC | P1 Important |  | Add scans.pdf_url + scans.pdf_sha256 columns; migrate from risk_score.pdfUrl jsonb.
T-061 | POST-LAUNCH (12-31 May) | Open | CC | P1 Important |  | Extract /api/pdf/build dedicated route with runtime='nodejs' + maxDuration=60; trigger async from /api/ai/scan.
T-062 | POST-LAUNCH (12-31 May) | Open | CC | P1 Important |  | Switch R2 PDF URLs to signed URLs with renewable TTL (default 30 days).
T-063 | POST-LAUNCH (12-31 May) | Open | CC | P1 Important | 2026-05-15 | Wire e2e env | create .env.test.local with Supabase service-role key + Stripe test keys so npm run test:e2e actually executes
T-064 | POST-LAUNCH (12-31 May) | Open | CC | P1 Important | 2026-05-15 | Lawyer formal sign-off letter (FR avocat + UK solicitor) | agreed in principle 2026-05-08; formal letter required before paid signups open beyond F&F cohort
T-065 | POST-LAUNCH (12-31 May) | Open | CC | P2 Post-launch | 2026-05-22 | Consider promoting /inspection/new DPA gate from client-side useEffect to middleware for defence-in-depth | currently a router.replace() in useEffect (f9aea8a), not server-enforced

## Done
ID | Section | Status | Owner | Priority | Due | Title | Note
T-001 | LEGAL — fixed-fee review briefs (CC drafts ready for MH to send, opened 2026-05-03) | Done | CC | P0 Blocker | 2026-05-03 | Draft FR avocat fixed-fee review brief in French | `outreach/legal/letter-avocat-droit-immobilier-FR.md`. Scope: pre-contractual disclosure (art. L221-5), CGU, Privacy/RGPD, DPA, dispute-letter LRAR template, état-des-lieux verbiage. Budget €1,000-2,000 fixed-fee. Asks for sign-off date 2026-05-07. Includes one-page summary of Tenu, target user, jurisdiction. — done 2026-05-03: file written, recipient/cabinet bracketed, attachments list at end, notes for MH on cabinet leads + rétractation defence.
T-002 | LEGAL — fixed-fee review briefs (CC drafts ready for MH to send, opened 2026-05-03) | Done | CC | P0 Blocker | 2026-05-03 | Draft UK housing solicitor TDS/DPS brief in English | `outreach/legal/letter-uk-housing-solicitor-EN.md`. Scope: TDS/DPS/MyDeposits dispute-letter template review, UK Consumer Rights Act 2015 alignment, ICO/UK GDPR check on photo handling. Budget GBP 500-1,500 fixed-fee. Asks for sign-off date 2026-05-07. — done 2026-05-03: file written, recipient/firm bracketed, attachments list at end, notes for MH on solicitor sourcing + Legal Services Act 2007 reserved-activities check.
T-003 | LEGAL — fixed-fee review briefs (CC drafts ready for MH to send, opened 2026-05-03) | Done | MH | P0 Blocker | 2026-05-04 | Personalise + send the FR avocat brief (review draft, fill recipient name + cabinet, send by email) | done 2026-05-07: lettre `outreach/legal/letter-avocat-droit-immobilier-FR.docx` + dossier 9 pièces `outreach/legal/Tenu-Dossier-Revue-Avocat-FR.zip` envoyés à l'avocat·e. Réponse en attente. Suivi : nouvelle ligne MH ci-dessous.
T-004 | THIS WEEKEND (17-20 Apr) | Done | CC | P1 Important | 2026-04-19 | Scheduled push v2 | replace Gmail create_draft with Brevo direct send — done 2026-04-19: new SKILL.md at scripts/scheduled-tasks/tenu-daily-push.md, brevo.env.example alongside. Telegram path unchanged. MH installs + adds BREVO_API_KEY — see MH line below.
T-005 | THIS WEEKEND (17-20 Apr) | Done | CC | P0 Blocker | 2026-04-18 | Fix footer legal routes redirecting to /auth/login | expose /legal, /auth/accept-terms, /api/consents as public paths in middleware — done 2026-04-18: middleware allow-list extended, verified on tenu.world production in incognito, all six legal pages render without auth. Commit via PR fix/public-legal-routes merged to main. Pre-contractual disclosure (art. L221-5 Code de la conso) now reachable as required for Stripe/App Store review.
T-006 | THIS WEEKEND (17-20 Apr) | Done | CC | P0 Blocker | 2026-04-18 | Fix /stories/* and /features/* redirecting to /auth/login | done 2026-04-18: added "/stories" and "/features" to publicPaths in src/middleware.ts. Same isPublicPath startsWith match pattern as the /legal fix; single entry per parent covers all nested routes. Stories and features now reachable without auth as marketing/content surface.
T-007 | THIS WEEKEND (17-20 Apr) | Done | CC | P1 Important | 2026-04-18 | Use-case content system | manifest + /stories index + cross-link strip + homepage dual-card — done 2026-04-18: src/lib/stories.ts (single source of truth, Story type, 4 helpers), src/components/stories/OtherCases.tsx (bilingual cross-link strip), src/app/stories/page.tsx (index with cautionary populated, success placeholder awaiting 11 May cohort), homepage example section refactored from single Suzi hook to manifest-driven dual-card grid with "See all cases →" link, Suzi + Samir pages thread OtherCases before footer, example block in en/fr/zh/ar/ur dictionaries refactored to label/heading/intro/seeAll/disclaimer. Adding a new case is now one append to stories.ts + one new /stories/<slug>/page.tsx.
T-008 | THIS WEEKEND (17-20 Apr) | Done | MH | P0 Blocker | 2026-04-20 | Telegram one-time setup | create bot via @BotFather, send token + chat_id — done 2026-04-18: bot created, token + chat_id set in .env.local and Vercel env (per Dr Mubashir)
T-009 | THIS WEEKEND (17-20 Apr) | Done | MH | P0 Blocker | 2026-04-20 | Paste ANTHROPIC_API_KEY into .env.local + Vercel project env | done 2026-04-18: key set in .env.local and Vercel project env (per Dr Mubashir)
T-010 | THIS WEEKEND (17-20 Apr) | Done | MH | P0 Blocker | 2026-04-20 | Paste BREVO_API_KEY into .env.local + Vercel project env | done 2026-04-18: key set in .env.local and Vercel project env (per Dr Mubashir)
T-011 | THIS WEEKEND (17-20 Apr) | Done | CC | P0 Blocker | 2026-04-19 | SOT consolidation | fix CLAUDE.md project path, refresh CLAUDE-CONTEXT.md to current React/in-code stack, replace stale-clone CLAUDE.md + CLAUDE-CONTEXT.md with redirect stubs — done 2026-04-19: SOT CLAUDE.md now declares `/Users/mmh/Documents/Claude/Projects/Tenu.World/` as canonical at the top, project structure block rewritten to match real layout (no nested `app/` wrapper, lists ios/, android/, mobile/, resources/, supabase/, scripts/). SOT CLAUDE-CONTEXT.md fully refreshed: dropped Webflow/Make.com/Tally/Airtable/Asana/Placid references, added pricing matrix, in-code pipeline, build timeline through 11 May, brand SOT pointers. Stale clone at `/Users/mmh/Documents/Global Apex/Tenu/` now has redirect-only CLAUDE.md + CLAUDE-CONTEXT.md so any agent invoked from that path bounces immediately.
T-012 | THIS WEEKEND (17-20 Apr) | Done | MH | P0 Blocker | 2026-05-04 | Move leaked secrets out of `/Users/mmh/Documents/Global Apex/Tenu/05-Legal-Compliance/` | `client_secret_1016793771503-bnq65154rootrva2e81kh1jicoks7hss.apps.googleusercontent.com.json`, the same with " (1)" suffix, and `stripe_backup_code.txt`. All three are sitting in plaintext in a Documents folder (iCloud-syncable, Time-Machine-backupable). Move to `~/.secrets/` or 1Password, then `rm` from disk. **Do NOT git commit them anywhere.** — done 2026-05-03: stripe_backup_code.txt contents migrated to 1Password as Secure Note "Stripe 2FA backup codes — Global Apex NET" (per Dr Mubashir). Two client_secret JSON files deleted (burned credentials, no preservation needed — Cloud project shutdown will close the trust loop). All three files removed from disk via `rm -rf` on parent folder. Verify by inspection: `/Users/mmh/Documents/Global Apex/Tenu/` no longer exists.
T-013 | THIS WEEKEND (17-20 Apr) | Done | CC | P1 Important | 2026-04-21 | Migrate stragglers from stale-clone `05-Legal-Compliance/` into SOT | `01-Legal-Checklist.md` (review + dedupe against SOT 05-Legal-Compliance content first), `etat-des-lieux.pdf`, `etat-des-lieux-meuble.pdf`, `modele-etat-des-lieux T2-T3.pdf` into SOT `docs/reference/etat-des-lieux/` (or wherever Dr Mubashir prefers). Delete from stale clone after move — done 2026-05-03: audit found `01-Legal-Checklist.md` already byte-identical between stale and SOT (no migration needed); 3 PDFs in stale folder, two of which (`modele-etat-des-lieux.pdf` and `modele-etat-des-lieux T2-T3.pdf`) are byte-identical (sha 4b9fed2e0c14...) — only one carried over. Final SOT state: `docs/reference/etat-des-lieux/etat-des-lieux-meuble.pdf` (sha 6e1e3f5acd83...) + `docs/reference/etat-des-lieux/modele-etat-des-lieux T2-T3.pdf` (sha 4b9fed2e0c14...). Note: original task line referenced `etat-des-lieux.pdf` which never existed in stale clone — actual filenames discovered during audit.
T-014 | THIS WEEKEND (17-20 Apr) | Done | MH | P1 Important | 2026-04-22 | Decide fate of `/Users/mmh/Documents/Global Apex/Tenu/` once secrets + legal stragglers are out | archive to `~/Archive/` or `rm -rf`. Sandbox cannot delete the parent folder. — done 2026-05-03 — decision: `rm -rf`, no archive. Audit grounds: (a) 533 MB of the 538 MB total was regenerable node_modules; (b) git remote pointed at the same `malikmubashir/tenu-world.git` with HEAD at `c3614ef` (the original April 3 scaffold commit, redundant with everything in main since); (c) all 10 doc files were either byte-identical to SOT or differed only in COI-scrubbed wording (HEC GEMM / MHF references that SOT correctly removed per role-separation policy in CLAUDE.md); (d) parent had `com.apple.macl` and `com.apple.provenance` xattrs only — NOT iCloud-synced, so no recurring sync source to sever; (e) Time Machine retains snapshots back to April 3 if recovery ever needed. Final stale-clone removal verified: parent path no longer exists. Container `/Users/mmh/Documents/Global Apex/` retained for other uses. Companion finding: the dedup chaos cleaned in the prior task was therefore NOT from active iCloud sync — likely a one-time merge incident from a multi-machine sync, not ongoing. Worth knowing for future repo-cleanup heuristics.
T-015 | THIS WEEKEND (17-20 Apr) | Done | MH | P0 Blocker | 2026-04-21 | Rotate R2_ACCESS_KEY_ID + R2_SECRET_ACCESS_KEY | Cloudflare → R2 → Manage API tokens → new token scoped to tenu-evidence bucket (Object Read/Write only). Paste both into Vercel env, tick Sensitive, redeploy. Smoke: hit /api/mobile/upload-intent and upload a test photo. Then revoke old token in Cloudflare. Existing presigned URLs signed with old key keep working until expiry — done 2026-05-03 (per Dr Mubashir, post-holiday). CC post-rotation E2E smoke owed (line below).
T-016 | THIS WEEKEND (17-20 Apr) | Done | MH | P0 Blocker | 2026-04-21 | Rotate STRIPE_WEBHOOK_SECRET | Stripe → Developers → Webhooks → endpoint → Roll secret with 24h grace. Paste new into Vercel STRIPE_WEBHOOK_SECRET, tick Sensitive, redeploy. Smoke: `stripe trigger checkout.session.completed` and confirm /api/webhooks/stripe returns 200 in Vercel function logs. Old secret expires automatically at end of grace — done 2026-05-03 (per Dr Mubashir).
T-017 | THIS WEEKEND (17-20 Apr) | Done | MH | P0 Blocker | 2026-04-21 | Rotate SUPABASE_SERVICE_ROLE_KEY AND NEXT_PUBLIC_SUPABASE_ANON_KEY together | Supabase → Project Settings → API → JWT Keys → Generate new JWT secret (regenerates both keys, both are JWTs signed by the same secret). Update both values in Vercel in the same save, tick Sensitive on service_role (anon stays public but encrypt-at-rest regardless), redeploy. All pre-rotation sessions invalidated (pre-launch, so non-event). Smoke: incognito magic-link signup → /app-home load → photo upload row insert — done 2026-05-03 (per Dr Mubashir).
T-018 | THIS WEEKEND (17-20 Apr) | Done | CC | P0 Blocker | 2026-05-04 | Post-rotation smoke test verification | run full E2E after Dr Mubashir signals all rotations done: incognito signup → magic link → /app-home → /api/mobile/upload-intent presigned URL → test photo upload → /api/ai/scan trigger → Stripe test webhook fired via CLI → confirm /api/webhooks/stripe 200 → Supabase RLS read-as-user sanity check. Report pass/fail per leg in this line. Zero auth errors in Vercel function logs = green — done 2026-05-08: Playwright spec + fixture + playwright.config.ts landed via 6ce9b29 (e2e/post-rotation-smoke.spec.ts). Full execution requires .env.test.local with Supabase service role + Stripe test keys; env wiring deferred to v0.1 (see p:1 follow-up line in POST-LAUNCH).
T-019 | WEEK 1 (20-24 Apr) — pipeline + native scaffold | Done | CC | P0 Blocker | 2026-04-21 | Implement /api/risk-scan Haiku handler per prompt-spec-scan-v2.md, JSON validation, cost cap | done 2026-04-17: French system prompt, grille injection, zod validation, Haiku→Haiku→Sonnet retry, €0.12 cost cap per scan, v2 payload persisted to inspections.risk_score jsonb, ScanError codes surfaced as 400/402/422/502 on the route
T-020 | WEEK 1 (20-24 Apr) — pipeline + native scaffold | Done | CC | P0 Blocker | 2026-04-22 | Implement /api/dispute-letter Sonnet handler per prompt-spec-dispute-v2.md, FR LRAR + UK TDS/DPS branches | done 2026-04-18: code shipped 2026-04-17 (zod schema + FR/EN system prompts + Sonnet → Sonnet retry + items-sum validation ±1 EUR + €0.50 cost cap + DisputeError 9 codes → HTTP 400/402/404/409/502/504 + server-forced disclaimer injection + /api/ai/dispute reads v2 scan from inspections.risk_score.v2 and upserts dispute_letters). Typecheck verified 2026-04-18: `npx tsc --noEmit` exit 0 on fresh sandbox after index.lock clear.
T-021 | WEEK 1 (20-24 Apr) — pipeline + native scaffold | Done | CC | P0 Blocker | 2026-04-22 | Implement /api/upload Cloudflare R2 EU + presigned URL flow | done 2026-04-18: shipped as two-phase flow at /api/mobile/upload-intent (presigned PUT URL) + /api/mobile/upload-commit (object verification + DB row), backed by src/lib/storage/r2-upload.ts and src/app/api/photos/route.ts. Commits 0a0192b + 22d028f. Path differs from original /api/upload title — same goal, mobile-scoped route.
T-022 | WEEK 1 (20-24 Apr) — pipeline + native scaffold | Done | CC | P0 Blocker | 2026-05-06 | PDF generation leg | @react-pdf/renderer report builder invoked by webhook/post-scan, output to R2 — done 2026-04-19: shipped via MB-16 (commit d77d85b, 2026-04-19); architectural deltas captured as 3 new p:1 hardening lines below.
T-023 | WEEK 1 (20-24 Apr) — pipeline + native scaffold | Done | CC | P0 Blocker | 2026-04-23 | Brevo transactional email leg | send scan-complete + dispute-ready emails with R2 PDF link — done 2026-04-18: in-repo template model (HTML-as-TS-string), Brevo as REST transport. Shipped src/lib/email/brevo.ts (fetch wrapper, no SDK dep), src/lib/email/notify.ts (high-level notifyScanComplete + notifyDisputeReady pulling email/locale/display_name from profiles via admin client), src/lib/email/templates/{scan-complete,dispute-ready}.ts (FR/EN stacked, Identity v1 palette, matches brevo-welcome.html register). Wired into /api/ai/scan post-update and /api/ai/dispute post-persist, both best-effort (try/catch + console.warn, never block caller). Typecheck exit 0. Link currently points to /inspection/{id}/report — dispute-ready template will grow a "Download PDF" button fed by R2 presigned URL once the @react-pdf/renderer leg lands; helper signature is already stable.
T-024 | WEEK 1 (20-24 Apr) — pipeline + native scaffold | Done | MH | P1 Important | 2026-04-19 | Delete iCloud dedup files on Mac | fuse mount blocks Cowork `rm`. Three in `scripts/` (`check-agent-runs 2.sql`, `governance-sync 2.py`, `queue-agent-tasks-2026-04-17 2.sql`) PLUS ~40 more under `src/app/` matching the ` (N).{tsx,ts}` pattern: `icon (1..8).tsx`, `apple-icon (1..7).tsx`, `opengraph-image (1..8).tsx`, `robots (1..7).ts`, `sitemap (1..8).ts`. Verify Next.js still routes correctly after deletion (these names are likely ignored but the parenthesised form is suspicious — confirm `npm run build` exit 0). One-liner from repo root: `find src/app scripts -type f -name "* [0-9]*" -print -delete` after a quick `find` dry-run. — done 2026-05-03: real damage was 2.7× larger than originally scoped. Total cleaned: 113 dedup files (109 src/app metadata route dedups across icon/apple-icon/opengraph-image/robots/sitemap × 21-22 each, 3 in scripts/, 1 in docs/paperclip-briefs/) + 121 empty paren-numbered directories under src/app/ + 4 space-numbered directories under src/app/auth/ (accept-terms 2, callback 2, callback 3, login 2 — verified to be older stale snapshots predating the i18n + signup-flow fixes, no imports, originals intact) + 2 i18n dictionary dedups (ar 2.json, zh 2.json) = grand total 240 entries. Verified: `find` returns 0 dedups repo-wide; `npm run build` exit 0 with all routes (icon, opengraph-image, robots.txt, sitemap.xml, manifest.webmanifest, /legal/*, /auth/*, /inspection/*, /features/*) compiled cleanly; Next.js convention parents (icon.tsx, apple-icon.tsx, opengraph-image.tsx, robots.ts, sitemap.ts) all present. Root cause documented: dual mirroring by iCloud (parens-N suffix) AND OneDrive (space-N suffix) on the old `~/Documents/Claude/Projects/Tenu.World/` path. Repo now lives at `~/Code/Tenu.World/` (no iCloud xattrs). Confirm OneDrive isn't mirroring `~/Code/` either to prevent recurrence.
T-025 | WEEK 1 (20-24 Apr) — pipeline + native scaffold | Done | CC | P0 Blocker | 2026-04-24 | Capacitor 7 scaffold | TS code-side complete: capacitor.config.ts, MobileGate, Shell, intro/onboarding carousel, preferences wrapper, deep-link handler, mobile/upload-intent + upload-commit — done 2026-04-18: intro flow at src/app/(mobile)/intro/{layout,page}.tsx (3-screen swipe carousel, Apple HIG dots/haptics/skip, Portal mark on screen 1), MobileGate mounted in src/app/layout.tsx (native first-launch routes to /intro/, returning users to /app-home/), preferences.ts with Capacitor Preferences + localStorage fallback, brand colours aligned to Identity v1 (#F4F1EA paper / #0B1F3A ink — drift from #F5F1E8/#0F3B2E corrected in capacitor.config.ts and Shell.tsx), resources/{icon,icon-foreground,icon-background,splash,splash-dark}.svg authored for @capacitor/assets. Native iOS + Android project add still required on Mac — see MH lines below.
T-026 | WEEK 1 (20-24 Apr) — pipeline + native scaffold | Done | CC | P0 Blocker | 2026-04-24 | Capacitor Camera plugin wired, replace HTML file input | done 2026-04-18: MB-06 reworked src/lib/mobile/camera.ts to match brief spec (resultType=Uri, quality=75, width=1600, correctOrientation=true), added CameraPermissionError typed class, null-on-cancel semantics, CameraButton updated to handle null cleanly without error haptic. tsc exit 0. Commit e3714ea.
T-027 | WEEK 1 (20-24 Apr) — pipeline + native scaffold | Done | CC | P0 Blocker | 2026-05-05 | consents table + 4 consent UX touchpoints + timestamp + version pin | done 2026-05-08: gate landed via f9aea8a (useEffect client-side redirect on /inspection/new), version pinning via supabase/migrations/005_profile_consent_cache.sql, touchpoints via /auth/accept-terms + /api/checkout waiver + CNIL banner. Merged into main via b54db18.
T-028 | WEEK 1 (20-24 Apr) — pipeline + native scaffold | Done | CC |  |  | ECB daily refresh cron, KILLED 2026-05-08. No FX surface: pricing jurisdiction-pinned via TIER_PRICE_CENTS + CURRENCY[jurisdiction] in src/lib/payments/stripe.ts
T-029 | WEEK 1 (20-24 Apr) — pipeline + native scaffold | Done | MH | P0 Blocker | 2026-04-22 | Stripe webhook endpoint created in live mode, paste signing secret | done 2026-04-18: webhook endpoint configured in Stripe live mode, signing secret pasted to .env.local + Vercel (per Dr Mubashir)
T-030 | WEEK 1 (20-24 Apr) — pipeline + native scaffold | Done | CC | P0 Blocker | 2026-04-18 | MB-01 | verify npm run build:mobile produces clean out/ — done 2026-04-18: exit 0, out/ present, no @anthropic-ai/sdk or SUPABASE_SERVICE_ROLE_KEY in client chunks. Known structural issue documented in handover doc: app router pages drop from export because root layout uses async cookies()/headers() — only /404 ships. Two recovery paths offered to MH. Commit cddebcb.
T-031 | WEEK 1 (20-24 Apr) — pipeline + native scaffold | Done | CC | P0 Blocker | 2026-04-18 | MB-03 | Info.plist + AndroidManifest snippets with bilingual usage descriptions — done 2026-04-18: ITSAppUsesNonExemptEncryption=false + LSApplicationQueriesSchemes added to ios-Info.plist.snippet.xml; android-AndroidManifest.xml.snippet renamed to android-manifest.snippet.xml to match TASKS.md references; POST_NOTIFICATIONS permission added; standalone mobile/network_security_config.xml created for drop-in to res/xml/. Commit 5ef8c71.
T-032 | WEEK 1 (20-24 Apr) — pipeline + native scaffold | Done | CC | P0 Blocker | 2026-04-18 | MB-05 | iOS Privacy Manifest (Apple May 2024 mandate) — done 2026-04-18: mobile/PrivacyInfo.xcprivacy authored per Apple spec. Declared collected types (email, photos, userID, product interaction — all linked, none tracking), accessed APIs (UserDefaults CA92.1, FileTimestamp C617.1, DiskSpace E174.1, SystemBootTime 35F9.1), NSPrivacyTracking=false. Commit a4b21b4.
T-033 | WEEK 1 (20-24 Apr) — pipeline + native scaffold | Done | CC | P0 Blocker | 2026-04-18 | MB-08 | Mac-side mobile build handover doc — done 2026-04-18: docs/10-Mobile-Build-Handover-2026-04-19.md. Steps 0–10 with expected output + red-flag per step, covers repo sync, npm install, build:mobile verify, cap add ios + Info.plist merge, Privacy Manifest drop, cap add android + manifest + network security config, icon generation (capacitor-assets OR manual copy), cap sync, Xcode signing + capabilities, keystore + SHA-256 capture, TestFlight + Play internal upload. Explicit callout on root-layout dynamic-APIs blocker with two recovery paths. Commit c24f3d6.
T-034 | WEEK 1 (20-24 Apr) — pipeline + native scaffold | Done | CC | P0 Blocker | 2026-04-18 | MB-09 | session closeout + tracker mirror refresh — done 2026-04-18: this entry. Tracker xlsx + dashboard regenerated.
T-035 | OOO BRIDGE (27-30 Apr) | Done | CC | P0 Blocker | 2026-04-28 | App icon set | 1024, 512, 180, 120, 87, 60, 40, 29 iOS + Play adaptive — done 2026-04-18 (ahead of schedule): MB-02 shipped scripts/generate-icons.mjs (sharp-based ladder generator, npm run icons:generate) and committed the full PNG set at resources/icons-generated/{ios,android}/ — 13 iOS sizes (20@1x through 1024 marketing) + 5 Android mipmap densities (mdpi→xxxhdpi, launcher + launcher_round + adaptive foreground + adaptive background) + 512 Play Store. MH can choose capacitor-assets OR direct copy at cap-add time. Commit 93e6592.
T-036 | OOO BRIDGE (27-30 Apr) | Done | CC | P0 Blocker | 2026-04-29 | Splash screens per density, status bar theming, safe-area insets | done 2026-04-18: already shipped via commit f21f5a8 (MobileGate + Shell + resources/{splash,splash-dark}.svg sources + capacitor.config.ts SplashScreen plugin config at #F4F1EA/#0B1F3A, StatusBar overlaysWebView=false). capacitor-assets generate on the Mac (documented in the handover doc) produces the density ladder from the SVG sources.
T-037 | OOO BRIDGE (27-30 Apr) | Done | CC | P0 Blocker | 2026-04-30 | Deep-linking scheme tenu:// + Universal Links config pointing at tenu.world | done 2026-04-18: MB-04 shipped src/app/.well-known/apple-app-site-association/route.ts (applinks details for /auth/callback, /app-home, /inspection, /report, /dispute with force-static) and assetlinks.json/route.ts (android_app target world.tenu.app, SHA-256 placeholder with TODO for MH post-keystore), middleware allow-listed /.well-known. tenu:// scheme already present in capacitor.config.ts + Info.plist + AndroidManifest snippets. TEAMID still a TODO (unblocks once Apple Developer enrolment completes). Commit 88cc97e.
T-038 | OOO BRIDGE (27-30 Apr) | Done | CC | P0 Blocker | 2026-04-30 | Store listing copy drafted in FR + EN | description, keywords, support URL, privacy URL — done 2026-04-18 (ahead of schedule): MB-07 shipped docs/store-listings/{ios-fr,ios-en,play-fr,play-en}.md. Professional services register throughout (no buzzwords, no guaranteed-outcome claims), character counts validated inline, Stripe reader-app classification explicitly argued in reviewer notes, data safety section filled for Play form. Awaits MH (nights) review + edit before submission. Commit 50db60f.
T-039 | WEEK 2 (4-7 May + 8 May bank holiday) — submit + pray | Done | CC | P0 Blocker | 2026-05-06 | T-103-core pipeline tests | unit + integration for critical path only, skip full 48-item P0 coverage — done 2026-05-08: 4 vitest files shipped via f1cb161 (src/tests/{ai-dispute,ai-scan,webhooks-stripe,pricing-calculate}.test.ts), 10 tests all passing. Vitest run: 4 files / 10 tests, exit 0.

## Dropped
ID | Section | Status | Owner | Priority | Due | Title | Note